## Home Summary
MOTHER-IN-LAW HOUSE - EXPENSE TRACKER
Project Overview
Total Budget: | KES 1,490,000
Total Spent: | KES 1,463,213
Balance Remaining: | KES 26,786
Budget Used: | 98.2%
M-Pesa Fees: | KES 16,771
Outstanding Amounts
Outstanding Balances: | KES 91,300
Unpaid Labor: | KES 10,600
Total Pending: | KES 101,900
Total Committed: | KES 1,565,113
Budget Used (Inclusive): | 105.04%
Effective Balance: | KES -75,113
Project Completion Estimate
Pending Purchases: | KES 184,910
Total Project Cost: | KES 1,750,023
Additional Funds Needed: | KES 260,023
Category Breakdown
Category | Amount Spent | M-Pesa Fees | Total Cost | Budget %
Building Materials | 475220 | 5949.5 | 481169.5 | 32.29%
Labor Costs | 348600 | 3988.5 | 352588.5 | 23.66%
Hardware Items | 276671 | 3325.5 | 279996.5 | 18.79%
Metal & Steel | 176310 | 2090.5 | 178400.5 | 11.97%
Miscellaneous | 90901.5 | 566 | 91467.5 | 6.14%
Workers Accommodation | 30960 | 315 | 31275 | 2.10%
Transport & Logistics | 21950 | 250 | 22200 | 1.49%
Utilities | 10730 | 115 | 10845 | 0.73%
Furniture & Fixtures | 10000 | 96 | 10096 | 0.68%
Utilities & Services | 5100 | 75 | 5175 | 0.35%

## Daily Expenses
Date | Category | Subcategory | Description | Amount | M-Pesa Fee | Total Cost | Vendor | Status
15/09/2025 | Miscellaneous | Religious/Spiritual | Project offering at beginning | 10000 | 96 | 10096 | Church/Religious Institution | PAID
15/09/2025 | Transport & Logistics | Worker Transport | Transport for the Workers | 2000 | 25 | 2025 | Local Transport | PAID
15/09/2025 | Transport & Logistics | Material Transport | Transport ballast | 2500 | 25 | 2525 | Transport Company | PAID
15/09/2025 | Transport & Logistics | Material Transport | Transport blocks | 2500 | 25 | 2525 | Transport Company | PAID
15/09/2025 | Workers Accommodation | Accommodation | Accommodation for the workers | 2000 | 25 | 2025 | Local Lodge | PAID
15/09/2025 | Workers Accommodation | Housing | House rented for the workers (monthly) | 4000 | 40 | 4040 | Property Owner | PAID
15/09/2025 | Workers Accommodation | Bedding | 3 mattresses @2500 each | 7500 | 75 | 7575 | Furniture Store | PAID
15/09/2025 | Building Materials | Sand | Sand - 14 tonnes | 9600 | 96 | 9696 | Sand Supplier | PAID
15/09/2025 | Building Materials | Ballast | Ballast 7 tonnes | 17150 | 171.5 | 17321.5 | Ballast Supplier | PAID
15/09/2025 | Building Materials | Blocks | Blocks 300@52 | 15600 | 171.5 | 15771.5 | Block Manufacturer | PAID
15/09/2025 | Building Materials | Cement | Simba cement 710 @50 bags | 35500 | 455 | 35955 | Cement Dealer | PAID
15/09/2025 | Hardware Items | Sealants | Calafiator 1 ltr @1800 | 1800 | 25 | 1825 | Hardware Store | PAID
15/09/2025 | Hardware Items | Tools | Metal spades 550 @ 2 | 1100 | 15 | 1115 | Hardware Store | PAID
15/09/2025 | Hardware Items | Protective | Polythene Papers rolls 2300 @ 2 | 4600 | 40 | 4640 | Hardware Store | PAID
15/09/2025 | Hardware Items | Reinforcement | Hoop Iron 200 #4kg | 800 | 10 | 810 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 4" 200 @ 5kg | 1000 | 10 | 1010 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 3" 200 @ 3kg | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 2.5" 200 @3kg | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Roofing | Roofing poles 3" 250 @ 8 | 2000 | 25 | 2025 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Roofing Nails 300 @ 3kg | 900 | 10 | 910 | Hardware Store | PAID
15/09/2025 | Hardware Items | Sealing | Rubber maroon 200 @ 3pckts | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Plumbing | Horse Pipe clear 0.5 X60ft @ 1400 | 1400 | 15 | 1415 | Hardware Store | PAID
15/09/2025 | Metal & Steel | Welding | Welding rods 650 @ 2 packets | 1300 | 15 | 1315 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretube 1.5 X 1.5 900 @ 23 pcs | 20700 | 355 | 21055 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 1.5 X 1 800@ 16 pcs | 12800 | 156 | 12956 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 0.75 X 0.75 500 @17pcs | 8500 | 96 | 8596 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Zed 0.75 850 @10pcs | 8500 | 96 | 8596 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 1 X 1 600@4pcs | 2400 | 25 | 2425 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Sheets | Blacksheet (18g) 3pcs 2400@3pcs | 7200 | 75 | 7275 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flatbar 0.5 X 0.125 850 @ 1pc | 850 | 10 | 860 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flatbar 0.75 X 0.125 450 @ 10pcs | 4500 | 40 | 4540 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Chappy 250 @ 3pcs | 750 | 10 | 760 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Round 16 100 @ 5ft | 500 | 5 | 505 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flat busy 0.75 " 120 @ 26 pcs | 3120 | 40 | 3160 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | T-bar 0.75 850 @ 1pc | 850 | 10 | 860 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Down stopper 120 @12pcs | 1440 | 15 | 1455 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Finishing | Sand Paper p36 100 @3ms | 300 | 5 | 305 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Cutting disk 250 @5pcs | 1250 | 15 | 1265 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Grinding disk 250 @ 2pcs | 500 | 5 | 505 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Paint | Undercoat paint 5 ltrs 1050 @ 1pc | 1050 | 15 | 1065 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Paint | Thinner 5ltrs 1450 @ 1pc | 1450 | 15 | 1465 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Brush 2" 150 @2pcs | 300 | 5 | 305 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Chappy Normal (complete) 650 @ 1pc | 650 | 10 | 660 | Metal Supplier | PAID
15/09/2025 | Labor Costs | Daily Labor | Jack | 2000 | 25 | 2025 | Worker | PAID
15/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
15/09/2025 | Miscellaneous | Lost Payment | Overpayment not refunded | 1000 | 10 | 1010 | Unknown | PAID
16/09/2025 | Labor Costs | Specialist Labor | Welder deposit | 12000 | 156 | 12156 | Welder | PAID
16/09/2025 | Hardware Items | Tools | Wheelbarrow | 4350 | 40 | 4390 | Hardware Store | PAID
16/09/2025 | Hardware Items | Plumbing | Tap 1/2" | 550 | 10 | 560 | Hardware Store | PAID
16/09/2025 | Hardware Items | Storage | Blue drum | 2600 | 25 | 2625 | Hardware Store | PAID
16/09/2025 | Hardware Items | Tools | Hacksaw 14" | 280 | 5 | 285 | Hardware Store | PAID
16/09/2025 | Building Materials | Doors & Windows | Door Frames 6 @ 1200 | 7200 | 75 | 7275 | Carpenter | PAID
16/09/2025 | Transport & Logistics | Worker Transport | Transport for two electricians to voi | 2700 | 25 | 2725 | Transport Service | PAID
16/09/2025 | Labor Costs | Daily Labor | Jack - Daily Labor | 2000 | 25 | 2025 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Fundi 1 - Daily Labor | 1300 | 15 | 1315 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Helper 1 - Daily Labor | 600 | 10 | 610 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Helper 2 - Daily Labor | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Specialist Labor | Electrician Labor for fixing wiring pipes and boxes | 10000 | 96 | 10096 | Electrician | PAID
17/09/2025 | Transport & Logistics | Worker Transport | Transport back to Nairobi | 2200 | 25 | 2225 | Transport Service | PAID
17/09/2025 | Hardware Items | Electrical | 15"X15" meterbox 1pc | 2300 | 25 | 2325 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 8-way ccu 1pc | 3500 | 40 | 3540 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 16pcs twin boxes | 800 | 10 | 810 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 13pcs single boxes | 450 | 5 | 455 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 60pcs 20mm conduits | 5400 | 75 | 5475 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 25mm conduits | 600 | 10 | 610 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 2pcs 32mm conduits | 520 | 10 | 530 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 80pcs 20mm couplers | 400 | 5 | 405 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 10pcs 25mm couplers | 200 | 5 | 205 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 32mm couplers | 105 | 5 | 110 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 32mm bends | 150 | 5 | 155 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 1pc masking tape | 250 | 5 | 255 | Electrical Supplier | PAID
17/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Workers Accommodation | Food | Food for the workers | 3260 | 40 | 3300 | Local Vendor | PAID
18/09/2025 | Metal & Steel | Hardware | Window locks 15 @120 | 1800 | 25 | 1825 | Metal Supplier | PAID
18/09/2025 | Metal & Steel | Sheets | Perforated sheet | 4400 | 40 | 4440 | Metal Supplier | PAID
18/09/2025 | Metal & Steel | Finishing | Body filler | 2200 | 25 | 2225 | Metal Supplier | PAID
18/09/2025 | Labor Costs | Daily Labor | Dennis | 1300 | 15 | 1315 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 5 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Specialist Labor | Digging the septic tank (paid 4000 of 16000) | 4000 | 40 | 4040 | Excavation Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1200 | 15 | 1215 | Worker | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs squaretube 3x3x3mm @ 6000 | 30000 | 355 | 30355 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs squaretube 3x2x2mm @ 3500 | 17500 | 171.5 | 17671.5 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 4pcs 1.5x1.5x1.5mm @ 1650 | 6600 | 75 | 6675 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs 1x1x1.5mm @ 950 | 4750 | 40 | 4790 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Welding | 2 packets welding rods @ 650 | 1300 | 15 | 1315 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Tools | 2pcs grinding disk 7" @ 250 | 500 | 5 | 505 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Paint | 4ltrs undercoat @ 1050 | 4200 | 40 | 4240 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Paint | 5ltrs thinner @ 1450 | 7250 | 75 | 7325 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Sheets | 2pcs plate 6x6 @ 6000 | 12000 | 156 | 12156 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs 0.75x0.75x18gm @ 500 | 2500 | 25 | 2525 | Metal Supplier | PAID
19/09/2025 | Hardware Items | Water Storage | 3,000 ltrs tank | 20000 | 171.5 | 20171.5 | Tank Supplier | PAID
20/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Specialist Labor | Excavation work payment | 5600 | 75 | 5675 | Excavation Worker | PAID
20/09/2025 | Utilities | Water | Water payment | 4400 | 40 | 4440 | Water Utility | PAID
20/09/2025 | Labor Costs | Specialist Labor | Plumber payment | 5000 | 40 | 5040 | Plumber | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs PPR Pipes 3/4 @ 350 | 3500 | 40 | 3540 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 20pcs PPR elbows 3/4 @ 40 | 800 | 10 | 810 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR female elbow 3/4 X 1/2" @ 90 | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs PPR Tee 25mm @ 40 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs PPR female Tee 25mm x 1/2" @ 90 | 270 | 5 | 275 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs connected stop cork @ 1200 | 2400 | 25 | 2425 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs Male adapters 25mm x 1/2" @ 90 | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs thread tape large @ 100 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Kitchen | 1pc Kitchen sink | 1850 | 25 | 1875 | Hardware Store | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs waste pipe 1 1/2" @ 500 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs inspection tee 1 1/2" @ 160 | 320 | 5 | 325 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 250ml tangit glue | 550 | 10 | 560 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs floor trap 4 way @ 550 | 1100 | 15 | 1115 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc floor trap 1 way | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs inspection bend 4" @ 380 | 760 | 10 | 770 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs waste bend 4" @ 250 | 750 | 10 | 760 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc vent cup 4" | 100 | 1 | 101 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 6pcs manhole cover 450x450mm @ 1200 | 7200 | 75 | 7275 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs bib tap @ 1200 | 2400 | 25 | 2425 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs Gate valve 3/4 @ 850 | 2550 | 25 | 2575 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 7pcs male adapters 25mm @ 100 | 700 | 10 | 710 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc gulley trap 4" | 250 | 5 | 255 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 4pcs waste pipe 4" @ 450 | 1800 | 25 | 1825 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs PPR pipe 1" @ 450 | 1350 | 15 | 1365 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR elbow 1" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR Tee 1" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Building Materials | Wood | 40ft 4x2 cypress @ 58 | 2320 | 25 | 2345 | Timber Supplier | PAID
20/09/2025 | Building Materials | Wood | 180ft 3x2 cypress @ 47 | 8460 | 96 | 8556 | Timber Supplier | PAID
20/09/2025 | Hardware Items | Fasteners | 4kg nails 5" @ 200 | 800 | 10 | 810 | Hardware Store | PAID
20/09/2025 | Hardware Items | Fasteners | 5kg binding @ 200 | 1000 | 10 | 1010 | Hardware Store | PAID
20/09/2025 | Hardware Items | Tools | 1pc mabati scissors | 1500 | 15 | 1515 | Hardware Store | PAID
20/09/2025 | Building Materials | Cement | 40 bags simba cement @ 720 | 28800 | 355 | 29155 | Cement Dealer | PAID
20/09/2025 | Hardware Items | Plumbing | 8pcs GT nipple 1/2" @ 30 | 240 | 5 | 245 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 7pcs GT socket 1/2" @ 30 | 210 | 5 | 215 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 8pcs GT plug 1/2" @ 50 | 400 | 5 | 405 | Plumbing Supplier | PAID
21/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Specialist Labor | Plumber payment | 10000 | 96 | 10096 | Plumber | PAID
21/09/2025 | Utilities | Water | Water payment | 180 | 5 | 185 | Water Utility | PAID
21/09/2025 | Transport & Logistics | Logistics | Deo logistics | 550 | 10 | 560 | Logistics Provider | PAID
21/09/2025 | Hardware Items | Plumbing | 4pcs waste pipe 4" @ 450 | 1800 | 25 | 1825 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 4pcs inspection tee 4" @ 250 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs inspection bend 4" @ 380 | 760 | 10 | 770 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs waste bend 4" @ 250 | 500 | 5 | 505 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc waste rest bend 4" x 2" | 220 | 5 | 225 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc waste coupling 4" | 150 | 5 | 155 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc Y junctions 4" | 150 | 5 | 155 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs PPR cap 25mm @ 40 | 80 | 1 | 81 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs PPR caps 1" @ 80 | 160 | 5 | 165 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 3pcs sink trap @ 100 | 300 | 5 | 305 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 6pcs male adapters 1" @ 100 | 600 | 10 | 610 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 6pcs female adapters 1" @ 100 | 600 | 10 | 610 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 250ml tangit glue | 550 | 10 | 560 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc valve 3/4" brass | 1000 | 10 | 1010 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 5m lay flat 1/2" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
22/09/2025 | Utilities | Water | Water 3000 ltrs @ 1250 | 3750 | 40 | 3790 | Water Utility | PAID
22/09/2025 | Building Materials | Wood | 220ft Faceboard 8X1 cypress @ 95 | 20900 | 355 | 21255 | Timber Supplier | PAID
22/09/2025 | Hardware Items | Fasteners | 3kg Roof Nails @ 300 | 900 | 10 | 910 | Hardware Store | PAID
22/09/2025 | Hardware Items | Roofing | 2pkts rubbers cups @ 100 | 200 | 5 | 205 | Hardware Store | PAID
22/09/2025 | Building Materials | Wood | 30ft 3X2 bluegum @ 35 | 1050 | 15 | 1065 | Timber Supplier | PAID
22/09/2025 | Building Materials | Wood | 50ft 6X1 bluegum @ 40 | 2000 | 25 | 2025 | Timber Supplier | PAID
22/09/2025 | Building Materials | Roofing | 15pcs 3mtr Iron sheets @ 1650 | 24750 | 355 | 25105 | Roofing Supplier | PAID
22/09/2025 | Building Materials | Roofing | 6pcs ridges maasai red @ 650 | 3900 | 40 | 3940 | Roofing Supplier | PAID
22/09/2025 | Hardware Items | Plumbing | 1pc PVC pipe 4" @ 1500 | 1500 | 15 | 1515 | Plumbing Supplier | PAID
22/09/2025 | Hardware Items | Electrical | 5pcs Dio @ 950 | 4750 | 40 | 4790 | Electrical Supplier | PAID
22/09/2025 | Building Materials | Wood | 40ft 6x9 @ 45 | 1800 | 25 | 1825 | Timber Supplier | PAID
22/09/2025 | Metal & Steel | Structure | 3pcs squaretube 1 1/2x1 @ 800 | 2400 | 25 | 2425 | Metal Supplier | PAID
22/09/2025 | Hardware Items | Hardware | 2 pairs flap hinges @ 150 | 300 | 5 | 305 | Hardware Store | PAID
22/09/2025 | Labor Costs | Specialist Labor | Welder payment | 10000 | 96 | 10096 | Welder | PAID
22/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Building Materials | Sand | Sand | 4550 | 40 | 4590 | Sand Supplier | PAID
23/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Utilities & Services | Water Connection | Water connection | 5100 | 75 | 5175 | Water Company | PAID
24/09/2025 | Hardware Items | Tools & Supplies | Rope | 750 | 10 | 760 | Hardware Store | PAID
24/09/2025 | Hardware Items | Roofing Materials | 2kg roofing nails @ 300 each | 600 | 10 | 610 | Hardware Store | PAID
24/09/2025 | Hardware Items | Roofing Materials | 2 packets roofing rubbers @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 4 | 1200 | 15 | 1215 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 5 | 600 | 10 | 610 | Worker | PAID
25/09/2025 | Labor Costs | Specialist Labor | Water connection labor | 8000 | 96 | 8096 | Labor Contractor | PAID
25/09/2025 | Transport & Logistics | Worker Transport | Transport | 600 | 10 | 610 | Transport Service | PAID
25/09/2025 | Transport & Logistics | Worker Transport | Fundi transport | 3500 | 40 | 3540 | Transport Service | PAID
25/09/2025 | Workers Accommodation | Meals | Fundi extra meal | 1000 | 10 | 1010 | Food Vendor | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 rolls PPR pipe 3/4 @ 5500 each | 11000 | 156 | 11156 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc tap @ 600 | 600 | 10 | 610 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I Tee 1/2 @ 50 each | 100 | 1 | 101 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I socket 1/2 @ 30 each | 60 | 1 | 61 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I bend 1/2 @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 4 pcs G.I elbow @ 30 each | 120 | 5 | 125 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 4 pcs G.I nipple 1/2 @ 30 each | 120 | 5 | 125 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs threadtape large @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 3 pcs G.I union 1/2 @ 100 each | 300 | 5 | 305 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 20 mtrs PPR pipe 1/2 @ 50 per meter | 1000 | 10 | 1010 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs reducer 3/4 x 1/2 @ 80 each | 160 | 5 | 165 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc gate valve 3/4 @ 850 | 850 | 10 | 860 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc G.I tee 3/4 @ 40 | 40 | 0 | 40 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs union 3/4 @ 130 each | 260 | 5 | 265 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc socket 1/2 @ 30 | 30 | 0 | 30 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc stop cock @ 1200 | 1200 | 15 | 1215 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs gate valve 1/2 @ 650 each | 1300 | 15 | 1315 | Hardware Store | PAID
25/09/2025 | Miscellaneous | Tips | Tip | 500 | 5 | 505 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | 8 fundis @ 1200 each | 9600 | 96 | 9696 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | 11 helpers @ 600 each | 6600 | 75 | 6675 | Worker | PAID
25/09/2025 | Miscellaneous | Not used for the project | Money taken for personal use and potential overcharges or unaccounted expenses. | 79401.5 | 455 | 79856.5 | Self | PAID
24/09/2025 | Labor Costs | Specialized Labor | Welder - final balance payment (18000 of 40000 total) | 18000 | 171.5 | 18171.5 | Welder | PAID
25/09/2025 | Labor Costs | Specialized Labor | Excavation Worker - final balance payment (6400 of 16000 total) | 6400 | 75 | 6475 | Excavation Worker | PAID
26/09/2025 | Labor Costs | Daily Labor | 3 Fundi @ 1300 each | 3900 | 40 | 3940 | Worker | PAID
26/09/2025 | Labor Costs | Daily Labor | 2 Fundi @ 1200 each | 2400 | 25 | 2425 | Worker | PAID
26/09/2025 | Labor Costs | Daily Labor | 5 helpers @ 600 each | 3000 | 25 | 3025 | Worker | PAID
26/09/2025 | Transport & Logistics | Transport | Transport on boda | 300 | 5 | 305 | Transport | PAID
26/09/2025 | Building Materials | Sand | Sand 14 tonnes | 9000 | 96 | 9096 | Supplier | PAID
26/09/2025 | Utilities | Water | Water | 1200 | 15 | 1215 | Supplier | PAID
26/09/2025 | Building Materials | Cement | 20 bags cement @ 720 each | 14400 | 156 | 14556 | Supplier | PAID
26/09/2025 | Hardware Items | Plumbing | 1 pc G.I union 3/4 @ 130 | 130 | 5 | 135 | Hardware Store | PAID
26/09/2025 | Hardware Items | Plumbing | 1 pc G.I R/Socket 3/4 x 1/2 @ 80 | 80 | 1 | 81 | Hardware Store | PAID
26/09/2025 | Hardware Items | Plumbing | 1 pc G.I play 1/2 @ 40 | 40 | 0 | 40 | Hardware Store | PAID
27/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | Fundi 4 | 1200 | 15 | 1215 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | Fundi 5 | 1200 | 15 | 1215 | Worker | PAID
27/09/2025 | Labor Costs | Daily Labor | 5 helpers @ 600 each | 3000 | 25 | 3025 | Worker | PAID
27/09/2025 | Workers Accommodation | Food | Meat for workers | 1000 | 10 | 1010 | Supplier | PAID
28/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
28/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
28/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
28/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
28/09/2025 | Labor Costs | Daily Labor | Fundi 4 | 1200 | 15 | 1215 | Worker | PAID
28/09/2025 | Labor Costs | Daily Labor | 4 helpers @ 600 each | 2400 | 25 | 2425 | Worker | PAID
29/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
29/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
29/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
29/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
29/09/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
29/09/2025 | Building Materials | Cement | 30 bags cement @ 720 each | 21600 | 355 | 21955 | Supplier | PAID
29/09/2025 | Building Materials | Stones | 262ft 6X9 stones @ 42 sh per ft | 11790 | 156 | 11946 | Supplier | PAID
30/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
30/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
30/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
30/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
30/09/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
30/09/2025 | Utilities | Water | Water | 1200 | 15 | 1215 | Supplier | PAID
01/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
01/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
01/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
01/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
01/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
02/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
02/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
02/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
02/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
02/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
02/10/2025 | Workers Accommodation | Food Supplies | Unga and cooking oil for workers | 2700 | 25 | 2725 | Supplier | PAID
02/10/2025 | Workers Accommodation | Food | Unga and cooking oil for workers | 2700 | 25 | 2725 | Supplier | PAID
03/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
03/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
03/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
03/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
03/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
04/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
04/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
04/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
04/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
04/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
04/10/2025 | Transport & Logistics | Transport | Transport | 1000 | 10 | 1010 | Transport Service | PAID
04/10/2025 | Building Materials | Wood | Timber 6X1 80ft @ 40 | 3200 | 40 | 3240 | Timber Supplier | PAID
04/10/2025 | Building Materials | Wood | Timber 3X2 20ft @ 35 | 700 | 10 | 710 | Timber Supplier | PAID
04/10/2025 | Building Materials | Cement | 50 bags cement @ 710 each | 35500 | 455 | 35955 | Cement Dealer | PAID
04/10/2025 | Hardware Items | Tools | 1 pc D10 @ 950 | 950 | 10 | 960 | Hardware Store | PAID
04/10/2025 | Hardware Items | Tools | 1 pc D8 @ 650 | 650 | 10 | 660 | Hardware Store | PAID
06/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
06/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
06/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
06/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
06/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
07/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
07/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
07/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
07/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
07/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
08/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
08/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
08/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
08/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
08/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
08/10/2025 | Building Materials | Wood | 2x2 timber 800ft @ 22 | 17600 | 171.5 | 17771.5 | Timber Supplier | PAID
08/10/2025 | Hardware Items | Ventilation | 2 window vents @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
08/10/2025 | Transport & Logistics | Transport | Transport | 200 | 5 | 205 | Transport Service | PAID
08/10/2025 | Hardware Items | Fasteners | 8kg nails 4" @ 200 | 1600 | 25 | 1625 | Hardware Store | PAID
08/10/2025 | Hardware Items | Fasteners | 10kg nails 3" @ 200 | 2000 | 25 | 2025 | Hardware Store | PAID
08/10/2025 | Hardware Items | Fasteners | 2 packets steel nail 3" @ 350 | 700 | 10 | 710 | Hardware Store | PAID
08/10/2025 | Hardware Items | Plumbing | 1 pc manhole cover 18x18 @ 1200 | 1200 | 15 | 1215 | Hardware Store | PAID
08/10/2025 | Hardware Items | Sealants | 2 pcs silicon clear @ 350 | 700 | 10 | 710 | Hardware Store | PAID
08/10/2025 | Hardware Items | Fasteners | 2kg nails 2.5" @ 200 | 400 | 5 | 405 | Hardware Store | PAID
09/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
09/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
09/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
09/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
09/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
10/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
10/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
10/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
10/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
10/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
10/10/2025 | Hardware Items | Electrical | Outside Ovals lights 4pcs @ 400 | 1600 | 25 | 1625 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Circle light 1 pc | 600 | 10 | 610 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Ball fitting + bulb 3 @ 550 | 1650 | 25 | 1675 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Sitting full moon light | 5000 | 40 | 5040 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Down lighters 22pcs @ 250 | 5500 | 75 | 5575 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Panel surface light 2 pcs @ 500 | 1000 | 10 | 1010 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | Kitchen diffuser | 700 | 10 | 710 | Electrical Store | PAID
10/10/2025 | Hardware Items | Electrical | 1.5 mm twin wire for down lighters 1 roll | 6500 | 75 | 6575 | Electrical Store | PAID
11/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
11/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
11/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
11/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
11/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
11/10/2025 | Hardware Items | Electrical | 1.5 mm red wire 3rolls @ 2650 | 7950 | 96 | 8046 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 1.5 mm blue wire 1roll @ 2650 | 2650 | 25 | 2675 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 1.5 mm green wire 1roll @ 2650 | 2650 | 25 | 2675 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 2.5 mm red wire 1roll @ 4350 | 4350 | 40 | 4390 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 2.5 mm green wire 1roll @ 4350 | 4350 | 40 | 4390 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 2.5 mm blue wire 1roll @ 4350 | 4350 | 40 | 4390 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 4.0mm red wire @ 90 | 900 | 10 | 910 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 4.0mm blue wire @ 90 | 900 | 10 | 910 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 4.0mm green wire @ 90 | 900 | 10 | 910 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 10.0mm red wire @ 240 | 2400 | 25 | 2425 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 10.0mm green wire @ 240 | 2400 | 25 | 2425 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 10m 10.0mm blue wire @ 240 | 2400 | 25 | 2425 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 2 pcs of 25mm bend @ 15 | 30 | 0 | 30 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 1 pc steel tape @ 350 | 350 | 5 | 355 | Electrical Store | PAID
11/10/2025 | Hardware Items | Electrical | 1 pc tape @ 150 | 150 | 5 | 155 | Electrical Store | PAID
12/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
12/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
12/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
12/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
12/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
12/10/2025 | Labor Costs | Specialist Labor | Electrician labor paid | 10000 | 96 | 10096 | Electrician | PAID
12/10/2025 | Transport & Logistics | Transport | Transport to Voi | 2600 | 25 | 2625 | Transport Service | PAID
12/10/2025 | Transport & Logistics | Transport | Transport for items bought in Nairobi | 400 | 5 | 405 | Transport Service | PAID
12/10/2025 | Transport & Logistics | Transport | Transport on motor bike | 300 | 5 | 305 | Transport Service | PAID
13/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
13/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
13/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
13/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
13/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
13/10/2025 | Hardware Items | Windows | Down payment for window panes and fixing (10000 paid, 17000 remaining) | 10000 | 96 | 10096 | Window Supplier | PAID
13/10/2025 | Building Materials | Wood | 2x2 pine timber @ 22 per unit (430 units) | 9460 | 96 | 9556 | Timber Supplier | PAID
13/10/2025 | Building Materials | Ceiling | 25pcs ceiling chip board 9mm @ 1050 | 26250 | 355 | 26605 | Building Supplier | PAID
13/10/2025 | Hardware Items | Fasteners | 5kg ceiling nails @ 230 | 1150 | 15 | 1165 | Hardware Store | PAID
13/10/2025 | Hardware Items | Fasteners | 5kg 4" nails @ 180 | 900 | 10 | 910 | Hardware Store | PAID
13/10/2025 | Hardware Items | Fasteners | 6kg 3" nails @ 180 | 1080 | 15 | 1095 | Hardware Store | PAID
13/10/2025 | Hardware Items | Fasteners | 2 packets steel nails @ 280 | 560 | 10 | 570 | Hardware Store | PAID
13/10/2025 | Hardware Items | Fasteners | 4kg 2" nails @ 180 | 720 | 10 | 730 | Hardware Store | PAID
13/10/2025 | Hardware Items | Fasteners | 2kg 1" nails @ 200 | 400 | 5 | 405 | Hardware Store | PAID
14/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
14/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
14/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
14/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
14/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
14/10/2025 | Workers Accommodation | Food | Workers food | 2700 | 25 | 2725 | Supplier | PAID
15/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
15/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
15/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
15/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
15/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
15/10/2025 | Workers Accommodation | Accommodation | Worker accommodation | 4100 | 40 | 4140 | Accommodation Provider | PAID
16/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
16/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
16/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
16/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
16/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
16/10/2025 | Hardware Items | Windows | Additional payment for windows (5000) and tinted glasses (2000) | 7000 | 75 | 7075 | Window Supplier | PAID
17/10/2025 | Hardware Items | Doors | 6 doors @ 3400 | 20400 | 355 | 20755 | Door Supplier | PAID
17/10/2025 | Hardware Items | Hardware | 18 hinges @ 250 | 4500 | 40 | 4540 | Hardware Store | PAID
17/10/2025 | Hardware Items | Hardware | 6 locks @ 1100 | 6600 | 75 | 6675 | Hardware Store | PAID
17/10/2025 | Building Materials | Wood | 3x1 Timber 80ft @ 35 | 2640 | 25 | 2665 | Timber Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 7 bags skim coat @ 1500 | 10500 | 156 | 10656 | Paint Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 2 20 ltrs undercoat @ 4700 | 9400 | 96 | 9496 | Paint Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 2 20ltrs superfast white @ 4500 | 9000 | 96 | 9096 | Paint Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 2x4ltrs Gun metal @ 3200 | 6400 | 75 | 6475 | Paint Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 4 ltrs clear varnish @ 1300 | 1300 | 15 | 1315 | Paint Supplier | PAID
17/10/2025 | Building Materials | Paint & Finishes | 5 ltrs white Spirit @ 1500 | 7500 | 75 | 7575 | Paint Supplier | PAID
17/10/2025 | Hardware Items | Tools | 6 mtrs sand paper p80 @ 100 | 600 | 10 | 610 | Hardware Store | PAID
17/10/2025 | Hardware Items | Tools | 8 mtrs sand paper p100 @ 100 | 800 | 10 | 810 | Hardware Store | PAID
17/10/2025 | Hardware Items | Tools | 2 pcs Roller brush @ 250 | 500 | 5 | 505 | Hardware Store | PAID
17/10/2025 | Hardware Items | Tools | 2 pcs wire brush @ 250 | 500 | 5 | 505 | Hardware Store | PAID
17/10/2025 | Building Materials | Tiles | 30 box floor tiles @ 1100 | 33000 | 355 | 33355 | Tile Supplier | PAID
17/10/2025 | Building Materials | Tiles | 20 box wall tiles @ 1100 | 22000 | 355 | 22355 | Tile Supplier | PAID
17/10/2025 | Building Materials | Cement | 15 bags Simba cement @ 720 | 10800 | 156 | 10956 | Cement Dealer | PAID
17/10/2025 | Building Materials | Wood | 8 Pcs mdf board @ 3700 | 29600 | 355 | 29955 | Timber Supplier | PAID
17/10/2025 | Hardware Items | Hardware | 21 pcs malpha hinges @ 150 | 3150 | 40 | 3190 | Hardware Store | PAID
17/10/2025 | Hardware Items | Adhesives | 1 ltr conta glue @ 1200 | 1200 | 15 | 1215 | Hardware Store | PAID
17/10/2025 | Hardware Items | Materials | 1 roll lipping @ 1300 | 1300 | 15 | 1315 | Hardware Store | PAID
17/10/2025 | Hardware Items | Fasteners | 2 box steel nails @ 300 | 600 | 10 | 610 | Hardware Store | PAID
17/10/2025 | Hardware Items | Fasteners | 1 box mdf screws 1" @ 500 | 500 | 5 | 505 | Hardware Store | PAID
17/10/2025 | Hardware Items | Hardware | 16 pcs handles @ 130 | 2080 | 25 | 2105 | Hardware Store | PAID
17/10/2025 | Hardware Items | Plumbing | 1 pc chrome pipe 1" @ 600 | 600 | 10 | 610 | Hardware Store | PAID
17/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
17/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
17/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
17/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
17/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
18/10/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
18/10/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
18/10/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
18/10/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
18/10/2025 | Labor Costs | Daily Labor | 3 helpers @ 600 each | 1800 | 25 | 1825 | Worker | PAID
18/10/2025 | Transport & Logistics | Transport | Transport | 600 | 10 | 610 | Transport Service | PAID
19/10/2025 | Labor Costs | Daily Labor | Jack - UNPAID | 1500 | 0 | 0 | Worker | UNPAID
19/10/2025 | Labor Costs | Daily Labor | Fundi 1 - UNPAID | 1300 | 0 | 0 | Worker | UNPAID
19/10/2025 | Labor Costs | Daily Labor | Fundi 2 - UNPAID | 1300 | 0 | 0 | Worker | UNPAID
19/10/2025 | Labor Costs | Daily Labor | 2 helpers @ 600 each - UNPAID | 1200 | 0 | 0 | Worker | UNPAID
20/10/2025 | Labor Costs | Daily Labor | Jack - UNPAID | 1500 | 0 | 0 | Worker | UNPAID
20/10/2025 | Labor Costs | Daily Labor | Fundi 1 - UNPAID | 1300 | 0 | 0 | Worker | UNPAID
20/10/2025 | Labor Costs | Daily Labor | Fundi 2 - UNPAID | 1300 | 0 | 0 | Worker | UNPAID
20/10/2025 | Labor Costs | Daily Labor | 2 helpers @ 600 each - UNPAID | 1200 | 0 | 0 | Worker | UNPAID
20/10/2025 | Hardware Items | Windows | Paid remaining balance for windows (total 13386) | 13386 | 156 | 13542 | Window Supplier | PAID
20/10/2025 | Furniture & Fixtures | Cabinet Work | Down payment for cabinet work | 10000 | 96 | 10096 | Cabinet Specialist | PAID

## M-Pesa Fees
M-Pesa Fee Analysis
Fee Structure
Amount Range | Fee (KES) | Transactions | Total Fees
7501-10000 | 96 | 18 | 1728
1501-3000 | 25 | 64 | 1600
3001-5000 | 40 | 28 | 1120
5001-7500 | 75 | 17 | 1275
15001-20000 | 171.5 | 6 | 1029
35001+ | 455 | 3 | 1365
1001-1500 | 15 | 152 | 2160
501-1000 | 10 | 90 | 900
20001-35000 | 355 | 11 | 3905
10001-15000 | 156 | 9 | 1404
101-500 | 5 | 56 | 280
50-100 | 1 | 5 | 5
0-49 | 0 | 4 | 0
Total M-Pesa Fees: | KES 16,771

## Outstanding Balances
OUTSTANDING BALANCES
Vendor | Description | Amount | Due Date
Electrician | Remaining balance for electrical work (8000 of 28000, paid 10000 on 12/10) | 8000 | To be scheduled
Plumber | Remaining balance for plumbing work (12000 of 27000) | 12000 | To be scheduled
Window Supplier | Window work fully paid (13386 paid on 20/10) | 0 | Completed
Painter | Painting work - 30000 | 30000 | To be scheduled
Cabinet Specialist | Original 16000 + unpaid work (3000 doors + 1800 curtain rods + 500 tip), paid 10000 down = 11300 remaining | 11300 | To be scheduled
Tile Fixer | Fixing tiles - 30000 | 30000 | To be scheduled
Total Outstanding: |  | KES 91,300

## Unpaid Labor
UNPAID LABOR EXPENSES
Date | Description | Amount | Status
19/10/2025 | Jack - UNPAID | 1500 | PENDING
19/10/2025 | Fundi 1 - UNPAID | 1300 | PENDING
19/10/2025 | Fundi 2 - UNPAID | 1300 | PENDING
19/10/2025 | 2 helpers @ 600 each - UNPAID | 1200 | PENDING
20/10/2025 | Jack - UNPAID | 1500 | PENDING
20/10/2025 | Fundi 1 - UNPAID | 1300 | PENDING
20/10/2025 | Fundi 2 - UNPAID | 1300 | PENDING
20/10/2025 | 2 helpers @ 600 each - UNPAID | 1200 | PENDING
Total Unpaid Labor: |  | KES 10,600

## Pending Purchases
PENDING PURCHASES (Not Yet Procured)
Category | Description | Amount
Plumbing & Fixtures | Toilets and mirrors | 25000
Electrical | Pending electrical equipment | 30000
Finishing & Decoration | Cornis | 15000
Paint | 4 ltrs silk Lagoon | 3000
Paint | 20 ltrs silk Ivory | 14700
Paint | 4 ltrs silk grey | 3000
Paint - Outside | 4 ltrs Aquatech white | 3200
Paint - Outside | 4 ltrs gloss black | 1200
Paint - Outside | 4 ltrs weatherguard ivory | 3200
Paint - Outside | 6 @ 4 ltrs weatherguard silicone @ 3200 each | 19200
Construction Work | Veranda works and other pending concrete work | 30000
Miscellaneous & Contingency | Estimated miscellaneous costs (15% of remaining work) - includes transport, food, accommodation, unexpected items | 37410
Total Pending Purchases: |  | KES 184,910
SUMMARY:
1. Already Spent (Paid): | KES 1,463,213
2. Outstanding Balances: | KES 91,300
3. Unpaid Labor: | KES 10,600
4. Pending Purchases: | KES 184,910
TOTAL PROJECT COST: | KES 1,750,023
Current Budget: | KES 1,490,000
Additional Funds Needed: | KES 260,023