## Home Summary
MOTHER-IN-LAW HOUSE - EXPENSE TRACKER
Project Overview
Total Budget: | KES 1,000,000
Total Spent: | KES 749,413
Balance Remaining: | KES 250,587
Budget Used: | 74.94%
M-Pesa Fees: | KES 8,668
Outstanding Amounts
Outstanding Balances: | KES 54,400
Unpaid Labor: | KES 0
Total Pending: | KES 54,400
Total Committed: | KES 803,813
Budget Used (Inclusive): | 80.38%
Effective Balance: | KES 196,187
Category Breakdown
Category | Amount Spent | M-Pesa Fees | Total Cost | Budget %
Labor Costs | 200900 | 2181 | 203081 | 20.31%
Building Materials | 183580 | 2300 | 185880 | 18.59%
Metal & Steel | 176310 | 2090.5 | 178400.5 | 17.84%
Hardware Items | 130215 | 1541.5 | 131756.5 | 13.18%
Workers Accommodation | 17760 | 190 | 17950 | 1.80%
Transport & Logistics | 16550 | 185 | 16735 | 1.67%
Utilities | 8330 | 85 | 8415 | 0.84%
Utilities & Services | 5100 | 75 | 5175 | 0.52%
Miscellaneous | 2000 | 20 | 2020 | 0.20%

## Daily Expenses
Date | Category | Subcategory | Description | Amount | M-Pesa Fee | Total Cost | Vendor | Status
15/09/2025 | Transport & Logistics | Worker Transport | Transport for the Workers | 2000 | 25 | 2025 | Local Transport | PAID
15/09/2025 | Transport & Logistics | Material Transport | Transport ballast | 2500 | 25 | 2525 | Transport Company | PAID
15/09/2025 | Transport & Logistics | Material Transport | Transport blocks | 2500 | 25 | 2525 | Transport Company | PAID
15/09/2025 | Workers Accommodation | Accommodation | Accommodation for the workers | 2000 | 25 | 2025 | Local Lodge | PAID
15/09/2025 | Workers Accommodation | Housing | House rented for the workers (monthly) | 4000 | 40 | 4040 | Property Owner | PAID
15/09/2025 | Workers Accommodation | Bedding | 3 mattresses @2500 each | 7500 | 75 | 7575 | Furniture Store | PAID
15/09/2025 | Building Materials | Sand | Sand - 14 tonnes | 9600 | 96 | 9696 | Sand Supplier | PAID
15/09/2025 | Building Materials | Ballast | Ballast 7 tonnes | 17150 | 171.5 | 17321.5 | Ballast Supplier | PAID
15/09/2025 | Building Materials | Blocks | Blocks 300@52 | 15600 | 171.5 | 15771.5 | Block Manufacturer | PAID
15/09/2025 | Building Materials | Cement | Simba cement 710 @50 bags | 35500 | 455 | 35955 | Cement Dealer | PAID
15/09/2025 | Hardware Items | Sealants | Calafiator 1 ltr @1800 | 1800 | 25 | 1825 | Hardware Store | PAID
15/09/2025 | Hardware Items | Tools | Metal spades 550 @ 2 | 1100 | 15 | 1115 | Hardware Store | PAID
15/09/2025 | Hardware Items | Protective | Polythene Papers rolls 2300 @ 2 | 4600 | 40 | 4640 | Hardware Store | PAID
15/09/2025 | Hardware Items | Reinforcement | Hoop Iron 200 #4kg | 800 | 10 | 810 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 4" 200 @ 5kg | 1000 | 10 | 1010 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 3" 200 @ 3kg | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Nails 2.5" 200 @3kg | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Roofing | Roofing poles 3" 250 @ 8 | 2000 | 25 | 2025 | Hardware Store | PAID
15/09/2025 | Hardware Items | Fasteners | Roofing Nails 300 @ 3kg | 900 | 10 | 910 | Hardware Store | PAID
15/09/2025 | Hardware Items | Sealing | Rubber maroon 200 @ 3pckts | 600 | 10 | 610 | Hardware Store | PAID
15/09/2025 | Hardware Items | Plumbing | Horse Pipe clear 0.5 X60ft @ 1400 | 1400 | 15 | 1415 | Hardware Store | PAID
15/09/2025 | Metal & Steel | Welding | Welding rods 650 @ 2 packets | 1300 | 15 | 1315 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretube 1.5 X 1.5 900 @ 23 pcs | 20700 | 355 | 21055 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 1.5 X 1 800@ 16 pcs | 12800 | 156 | 12956 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 0.75 X 0.75 500 @17pcs | 8500 | 96 | 8596 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Zed 0.75 850 @10pcs | 8500 | 96 | 8596 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | Squaretubes 1 X 1 600@4pcs | 2400 | 25 | 2425 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Sheets | Blacksheet (18g) 3pcs 2400@3pcs | 7200 | 75 | 7275 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flatbar 0.5 X 0.125 850 @ 1pc | 850 | 10 | 860 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flatbar 0.75 X 0.125 450 @ 10pcs | 4500 | 40 | 4540 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Chappy 250 @ 3pcs | 750 | 10 | 760 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Round 16 100 @ 5ft | 500 | 5 | 505 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Bars | Flat busy 0.75 " 120 @ 26 pcs | 3120 | 40 | 3160 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Structure | T-bar 0.75 850 @ 1pc | 850 | 10 | 860 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Down stopper 120 @12pcs | 1440 | 15 | 1455 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Finishing | Sand Paper p36 100 @3ms | 300 | 5 | 305 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Cutting disk 250 @5pcs | 1250 | 15 | 1265 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Grinding disk 250 @ 2pcs | 500 | 5 | 505 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Paint | Undercoat paint 5 ltrs 1050 @ 1pc | 1050 | 15 | 1065 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Paint | Thinner 5ltrs 1450 @ 1pc | 1450 | 15 | 1465 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Tools | Brush 2" 150 @2pcs | 300 | 5 | 305 | Metal Supplier | PAID
15/09/2025 | Metal & Steel | Accessories | Chappy Normal (complete) 650 @ 1pc | 650 | 10 | 660 | Metal Supplier | PAID
15/09/2025 | Labor Costs | Daily Labor | Jack | 2000 | 25 | 2025 | Worker | PAID
15/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
15/09/2025 | Miscellaneous | Lost Payment | Overpayment not refunded | 1000 | 10 | 1010 | Unknown | PAID
16/09/2025 | Labor Costs | Specialist Labor | Welder deposit | 12000 | 156 | 12156 | Welder | PAID
16/09/2025 | Hardware Items | Tools | Wheelbarrow | 4350 | 40 | 4390 | Hardware Store | PAID
16/09/2025 | Hardware Items | Plumbing | Tap 1/2" | 550 | 10 | 560 | Hardware Store | PAID
16/09/2025 | Hardware Items | Storage | Blue drum | 2600 | 25 | 2625 | Hardware Store | PAID
16/09/2025 | Hardware Items | Tools | Hacksaw 14" | 280 | 5 | 285 | Hardware Store | PAID
16/09/2025 | Building Materials | Doors & Windows | Door Frames 6 @ 1200 | 7200 | 75 | 7275 | Carpenter | PAID
16/09/2025 | Transport & Logistics | Worker Transport | Transport for two electricians to voi | 2700 | 25 | 2725 | Transport Service | PAID
16/09/2025 | Labor Costs | Daily Labor | Jack - Daily Labor | 2000 | 25 | 2025 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Fundi 1 - Daily Labor | 1300 | 15 | 1315 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Helper 1 - Daily Labor | 600 | 10 | 610 | Worker | PAID
16/09/2025 | Labor Costs | Daily Labor | Helper 2 - Daily Labor | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Specialist Labor | Electrician Labor for fixing wiring pipes and boxes | 10000 | 96 | 10096 | Electrician | PAID
17/09/2025 | Transport & Logistics | Worker Transport | Transport back to Nairobi | 2200 | 25 | 2225 | Transport Service | PAID
17/09/2025 | Hardware Items | Electrical | 15"X15" meterbox 1pc | 2300 | 25 | 2325 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 8-way ccu 1pc | 3500 | 40 | 3540 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 16pcs twin boxes | 800 | 10 | 810 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 13pcs single boxes | 450 | 5 | 455 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 60pcs 20mm conduits | 5400 | 75 | 5475 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 25mm conduits | 600 | 10 | 610 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 2pcs 32mm conduits | 520 | 10 | 530 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 80pcs 20mm couplers | 400 | 5 | 405 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 10pcs 25mm couplers | 200 | 5 | 205 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 32mm couplers | 105 | 5 | 110 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 3pcs 32mm bends | 150 | 5 | 155 | Electrical Supplier | PAID
17/09/2025 | Hardware Items | Electrical | 1pc masking tape | 250 | 5 | 255 | Electrical Supplier | PAID
17/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
17/09/2025 | Workers Accommodation | Food | Food for the workers | 3260 | 40 | 3300 | Local Vendor | PAID
18/09/2025 | Metal & Steel | Hardware | Window locks 15 @120 | 1800 | 25 | 1825 | Metal Supplier | PAID
18/09/2025 | Metal & Steel | Sheets | Perforated sheet | 4400 | 40 | 4440 | Metal Supplier | PAID
18/09/2025 | Metal & Steel | Finishing | Body filler | 2200 | 25 | 2225 | Metal Supplier | PAID
18/09/2025 | Labor Costs | Daily Labor | Dennis | 1300 | 15 | 1315 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Daily Labor | Helper 5 | 600 | 10 | 610 | Worker | PAID
18/09/2025 | Labor Costs | Specialist Labor | Digging the septic tank (paid 4000 of 16000) | 4000 | 40 | 4040 | Excavation Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
19/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1200 | 15 | 1215 | Worker | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs squaretube 3x3x3mm @ 6000 | 30000 | 355 | 30355 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs squaretube 3x2x2mm @ 3500 | 17500 | 171.5 | 17671.5 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 4pcs 1.5x1.5x1.5mm @ 1650 | 6600 | 75 | 6675 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs 1x1x1.5mm @ 950 | 4750 | 40 | 4790 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Welding | 2 packets welding rods @ 650 | 1300 | 15 | 1315 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Tools | 2pcs grinding disk 7" @ 250 | 500 | 5 | 505 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Paint | 4ltrs undercoat @ 1050 | 4200 | 40 | 4240 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Paint | 5ltrs thinner @ 1450 | 7250 | 75 | 7325 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Sheets | 2pcs plate 6x6 @ 6000 | 12000 | 156 | 12156 | Metal Supplier | PAID
19/09/2025 | Metal & Steel | Structure | 5pcs 0.75x0.75x18gm @ 500 | 2500 | 25 | 2525 | Metal Supplier | PAID
19/09/2025 | Hardware Items | Water Storage | 3,000 ltrs tank | 20000 | 171.5 | 20171.5 | Tank Supplier | PAID
20/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
20/09/2025 | Labor Costs | Specialist Labor | Excavation work payment | 5600 | 75 | 5675 | Excavation Worker | PAID
20/09/2025 | Utilities | Water | Water payment | 4400 | 40 | 4440 | Water Utility | PAID
20/09/2025 | Labor Costs | Specialist Labor | Plumber payment | 5000 | 40 | 5040 | Plumber | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs PPR Pipes 3/4 @ 350 | 3500 | 40 | 3540 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 20pcs PPR elbows 3/4 @ 40 | 800 | 10 | 810 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR female elbow 3/4 X 1/2" @ 90 | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs PPR Tee 25mm @ 40 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs PPR female Tee 25mm x 1/2" @ 90 | 270 | 5 | 275 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs connected stop cork @ 1200 | 2400 | 25 | 2425 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs Male adapters 25mm x 1/2" @ 90 | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 10pcs thread tape large @ 100 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Kitchen | 1pc Kitchen sink | 1850 | 25 | 1875 | Hardware Store | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs waste pipe 1 1/2" @ 500 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs inspection tee 1 1/2" @ 160 | 320 | 5 | 325 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 250ml tangit glue | 550 | 10 | 560 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs floor trap 4 way @ 550 | 1100 | 15 | 1115 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc floor trap 1 way | 450 | 5 | 455 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs inspection bend 4" @ 380 | 760 | 10 | 770 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs waste bend 4" @ 250 | 750 | 10 | 760 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc vent cup 4" | 100 | 1 | 101 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 6pcs manhole cover 450x450mm @ 1200 | 7200 | 75 | 7275 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 2pcs bib tap @ 1200 | 2400 | 25 | 2425 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs Gate valve 3/4 @ 850 | 2550 | 25 | 2575 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 7pcs male adapters 25mm @ 100 | 700 | 10 | 710 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 1pc gulley trap 4" | 250 | 5 | 255 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 4pcs waste pipe 4" @ 450 | 1800 | 25 | 1825 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 3pcs PPR pipe 1" @ 450 | 1350 | 15 | 1365 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR elbow 1" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 5pcs PPR Tee 1" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
20/09/2025 | Building Materials | Wood | 40ft 4x2 cypress @ 58 | 2320 | 25 | 2345 | Timber Supplier | PAID
20/09/2025 | Building Materials | Wood | 180ft 3x2 cypress @ 47 | 8460 | 96 | 8556 | Timber Supplier | PAID
20/09/2025 | Hardware Items | Fasteners | 4kg nails 5" @ 200 | 800 | 10 | 810 | Hardware Store | PAID
20/09/2025 | Hardware Items | Fasteners | 5kg binding @ 200 | 1000 | 10 | 1010 | Hardware Store | PAID
20/09/2025 | Hardware Items | Tools | 1pc mabati scissors | 1500 | 15 | 1515 | Hardware Store | PAID
20/09/2025 | Building Materials | Cement | 40 bags simba cement @ 720 | 28800 | 355 | 29155 | Cement Dealer | PAID
20/09/2025 | Hardware Items | Plumbing | 8pcs GT nipple 1/2" @ 30 | 240 | 5 | 245 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 7pcs GT socket 1/2" @ 30 | 210 | 5 | 215 | Plumbing Supplier | PAID
20/09/2025 | Hardware Items | Plumbing | 8pcs GT plug 1/2" @ 50 | 400 | 5 | 405 | Plumbing Supplier | PAID
21/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
21/09/2025 | Labor Costs | Specialist Labor | Plumber payment | 10000 | 96 | 10096 | Plumber | PAID
21/09/2025 | Utilities | Water | Water payment | 180 | 5 | 185 | Water Utility | PAID
21/09/2025 | Transport & Logistics | Logistics | Deo logistics | 550 | 10 | 560 | Logistics Provider | PAID
21/09/2025 | Hardware Items | Plumbing | 4pcs waste pipe 4" @ 450 | 1800 | 25 | 1825 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 4pcs inspection tee 4" @ 250 | 1000 | 10 | 1010 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs inspection bend 4" @ 380 | 760 | 10 | 770 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs waste bend 4" @ 250 | 500 | 5 | 505 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc waste rest bend 4" x 2" | 220 | 5 | 225 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc waste coupling 4" | 150 | 5 | 155 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc Y junctions 4" | 150 | 5 | 155 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs PPR cap 25mm @ 40 | 80 | 1 | 81 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 2pcs PPR caps 1" @ 80 | 160 | 5 | 165 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 3pcs sink trap @ 100 | 300 | 5 | 305 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 6pcs male adapters 1" @ 100 | 600 | 10 | 610 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 6pcs female adapters 1" @ 100 | 600 | 10 | 610 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 250ml tangit glue | 550 | 10 | 560 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 1pc valve 3/4" brass | 1000 | 10 | 1010 | Plumbing Supplier | PAID
21/09/2025 | Hardware Items | Plumbing | 5m lay flat 1/2" @ 80 | 400 | 5 | 405 | Plumbing Supplier | PAID
22/09/2025 | Utilities | Water | Water 3000 ltrs @ 1250 | 3750 | 40 | 3790 | Water Utility | PAID
22/09/2025 | Building Materials | Wood | 220ft Faceboard 8X1 cypress @ 95 | 20900 | 355 | 21255 | Timber Supplier | PAID
22/09/2025 | Hardware Items | Fasteners | 3kg Roof Nails @ 300 | 900 | 10 | 910 | Hardware Store | PAID
22/09/2025 | Hardware Items | Roofing | 2pkts rubbers cups @ 100 | 200 | 5 | 205 | Hardware Store | PAID
22/09/2025 | Building Materials | Wood | 30ft 3X2 bluegum @ 35 | 1050 | 15 | 1065 | Timber Supplier | PAID
22/09/2025 | Building Materials | Wood | 50ft 6X1 bluegum @ 40 | 2000 | 25 | 2025 | Timber Supplier | PAID
22/09/2025 | Building Materials | Roofing | 15pcs 3mtr Iron sheets @ 1650 | 24750 | 355 | 25105 | Roofing Supplier | PAID
22/09/2025 | Building Materials | Roofing | 6pcs ridges maasai red @ 650 | 3900 | 40 | 3940 | Roofing Supplier | PAID
22/09/2025 | Hardware Items | Plumbing | 1pc PVC pipe 4" @ 1500 | 1500 | 15 | 1515 | Plumbing Supplier | PAID
22/09/2025 | Hardware Items | Electrical | 5pcs Dio @ 950 | 4750 | 40 | 4790 | Electrical Supplier | PAID
22/09/2025 | Building Materials | Wood | 40ft 6x9 @ 45 | 1800 | 25 | 1825 | Timber Supplier | PAID
22/09/2025 | Metal & Steel | Structure | 3pcs squaretube 1 1/2x1 @ 800 | 2400 | 25 | 2425 | Metal Supplier | PAID
22/09/2025 | Hardware Items | Hardware | 2 pairs flap hinges @ 150 | 300 | 5 | 305 | Hardware Store | PAID
22/09/2025 | Labor Costs | Specialist Labor | Welder payment | 10000 | 96 | 10096 | Welder | PAID
22/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1200 | 15 | 1215 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
22/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Building Materials | Sand | Sand | 4550 | 40 | 4590 | Sand Supplier | PAID
23/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
23/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Utilities & Services | Water Connection | Water connection | 5100 | 75 | 5175 | Water Company | PAID
24/09/2025 | Hardware Items | Tools & Supplies | Rope | 750 | 10 | 760 | Hardware Store | PAID
24/09/2025 | Hardware Items | Roofing Materials | 2kg roofing nails @ 300 each | 600 | 10 | 610 | Hardware Store | PAID
24/09/2025 | Hardware Items | Roofing Materials | 2 packets roofing rubbers @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 1 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 2 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 3 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 4 | 600 | 10 | 610 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Fundi 4 | 1200 | 15 | 1215 | Worker | PAID
24/09/2025 | Labor Costs | Daily Labor | Helper 5 | 600 | 10 | 610 | Worker | PAID
25/09/2025 | Labor Costs | Specialist Labor | Water connection labor | 8000 | 96 | 8096 | Labor Contractor | PAID
25/09/2025 | Transport & Logistics | Worker Transport | Transport | 600 | 10 | 610 | Transport Service | PAID
25/09/2025 | Transport & Logistics | Worker Transport | Fundi transport | 3500 | 40 | 3540 | Transport Service | PAID
25/09/2025 | Workers Accommodation | Meals | Fundi extra meal | 1000 | 10 | 1010 | Food Vendor | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 rolls PPR pipe 3/4 @ 5500 each | 11000 | 156 | 11156 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc tap @ 600 | 600 | 10 | 610 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I Tee 1/2 @ 50 each | 100 | 1 | 101 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I socket 1/2 @ 30 each | 60 | 1 | 61 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs G.I bend 1/2 @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 4 pcs G.I elbow @ 30 each | 120 | 5 | 125 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 4 pcs G.I nipple 1/2 @ 30 each | 120 | 5 | 125 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs threadtape large @ 100 each | 200 | 5 | 205 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 3 pcs G.I union 1/2 @ 100 each | 300 | 5 | 305 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 20 mtrs PPR pipe 1/2 @ 50 per meter | 1000 | 10 | 1010 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs reducer 3/4 x 1/2 @ 80 each | 160 | 5 | 165 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc gate valve 3/4 @ 850 | 850 | 10 | 860 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc G.I tee 3/4 @ 40 | 40 | 0 | 40 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs union 3/4 @ 130 each | 260 | 5 | 265 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc socket 1/2 @ 30 | 30 | 0 | 30 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 1 pc stop cock @ 1200 | 1200 | 15 | 1215 | Hardware Store | PAID
25/09/2025 | Hardware Items | Plumbing Supplies | 2 pcs gate valve 1/2 @ 650 each | 1300 | 15 | 1315 | Hardware Store | PAID
25/09/2025 | Miscellaneous | Tips | Tip | 500 | 5 | 505 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Jack | 1500 | 15 | 1515 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 1 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 2 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | Fundi 3 | 1300 | 15 | 1315 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | 8 fundis @ 1200 each | 9600 | 96 | 9696 | Worker | PAID
25/09/2025 | Labor Costs | Daily Labor | 11 helpers @ 600 each | 6600 | 75 | 6675 | Worker | PAID
25/09/2025 | Labor Costs | Labor Payment | Payment of all accumulated unpaid labor | 52600 | 455 | 53055 | Workers | PAID
25/09/2025 | Miscellaneous | Transaction Fees | M-Pesa processing fees for labor payments | 500 | 5 | 505 | M-Pesa | PAID

## M-Pesa Fees
M-Pesa Fee Analysis
Fee Structure
Amount Range | Fee (KES) | Transactions | Total Fees
1501-3000 | 25 | 26 | 650
3001-5000 | 40 | 19 | 760
5001-7500 | 75 | 10 | 750
7501-10000 | 96 | 9 | 864
15001-20000 | 171.5 | 4 | 686
35001+ | 455 | 2 | 910
1001-1500 | 15 | 49 | 735
501-1000 | 10 | 69 | 690
20001-35000 | 355 | 5 | 1775
10001-15000 | 156 | 4 | 624
101-500 | 5 | 44 | 220
50-100 | 1 | 4 | 4
0-49 | 0 | 2 | 0
Total M-Pesa Fees: | KES 8,668

## Outstanding Balances
OUTSTANDING BALANCES
Vendor | Description | Amount | Due Date
Welder | Remaining balance for welding work (18000 of 40000) | 18000 | 24/09/2025
Excavation Worker | Remaining balance for septic tank digging (6400 of 16000) | 6400 | To be scheduled
Electrician | Remaining balance for electrical work (18000 of 28000) | 18000 | To be scheduled
Plumber | Remaining balance for plumbing work (12000 of 27000) | 12000 | To be scheduled
Total Outstanding: |  | KES 54,400

## Unpaid Labor
UNPAID LABOR EXPENSES
Date | Description | Amount | Status
Total Unpaid Labor: |  | KES 0